## M81 1+3
Month | NTP + | 32 |  |  |  | M81 Bang Yai-Kanchanaburi Intercity Motorway Project
Work Week Starting Date: | 2025-10-06
|  | Work Location |  |  |  |  | Date |  | Week | [6 empty] | Special Instruction |  | Leader |  |  | หมายเหตู
Activity Inst or T&C | Subsystem | CCD/TCB/CCB | Area | STA. | ตอนสัญญา | Description | Start | End | M O N | T U E | W E D | T H U | F R I | S A T | S U N |  | Other | Name | Company Name | Contact Number
Week 0(WK No.40) | [6 empty] | 2025-10-06 | 2025-10-12 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12
INST
INST
INST
Week 1(WK No.41) | [6 empty] | 2025-10-13 | 2025-10-19 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19
INST
INST
INST
Week 2 (WK No.42) | [6 empty] | 2025-10-20 | 2025-10-26 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26
INST
INST
INST
Week 3 (WK No.43) | [6 empty] | 2025-10-27 | 2025-11-02 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02
INST
INST
INST
Formulas:
End = [Date]+6
Week = [Date]
T U E = [Week]+1

## M6 1+3
Month | NTP + | 25 |  |  |  | M6 Bang Pa-in - Nakhon Ratchasima Intercity Motorway Project
Work Week Starting Date: | 2025-10-06
|  | Work Location |  |  |  |  | Date |  | Week | [6 empty] | Special Instruction |  | Leader |  |  | หมายเหตู
Activity Inst or T&C | Subsystem | CCD/TCB/CCB | Area | STA. | ตอนสัญญา | รายละเอียดงาน | Start | End | M O N | T U E | W E D | T H U | F R I | S A T | S U N |  | Other | Name | Company Name | Contact Number
Week 0(WK No.40) | [6 empty] | 2025-10-06 | 2025-10-12 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12
INST | [5 empty] | งาน Roadside
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 งาน Cabling (Roadside) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 งาน Steel Pole (Roadside) | 2025-10-06 | 2025-10-06 | Y | [8 empty] | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 ติดตั้ง Equipment (Roadside) | 2025-10-06 | 2025-10-12 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 ติดตั้ง Equipment (Roadside) | 2025-10-06 | 2025-10-12 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Cabling (Roadside) | 2025-10-08 | 2025-10-12 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Steel Pole (Roadside) | 2025-10-12 | 2025-10-12 | [6 empty] | Y |  |  | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST | [17 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | [5 empty] | งาน Scale House
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-6 ติดตั้ง Rack 42U (Scale House) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Rack 42U (Scale House) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 งาน Cabling (Scale House) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 งาน Demco (Scale House) | 2025-10-07 | 2025-10-10 |  | Y | Y | Y | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Rack 42U (Scale House) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Cabling (Scale House) | 2025-10-08 | 2025-10-12 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 ติดตั้ง Rack 42U (Scale House) | 2025-10-06 | 2025-10-07 | Y | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 ติดตั้ง Equipment (Scale House) | 2025-10-06 | 2025-10-12 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 ติดตั้ง Equipment (Scale House) | 2025-10-06 | 2025-10-12 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | [17 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
Week 1(WK No.41) | [6 empty] | 2025-10-13 | 2025-10-19 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19
INST | [5 empty] | งาน Roadside
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 ติดตั้ง Equipment (Roadside) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 Loxley ตรวจ Internal Equipment (Roadside) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 BGSR ตรวจ Official Equipment (Roadside) | 2025-10-16 | 2025-10-16 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 ติดตั้ง Equipment (Roadside) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 Loxley ตรวจ Internal Equipment (Roadside) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 BGSR ตรวจ Official Equipment (Roadside) | 2025-10-16 | 2025-10-16 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Cabling (Roadside) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Steel Pole (Roadside) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 Loxley ตรวจ Internal Cabling (Roadside) | 2025-10-15 | 2025-10-15 |  |  | Y | [6 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 BGSR ตรวจ Official Cabling (Roadside) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Roadside) | 2025-10-17 | 2025-10-19 |  |  |  |  | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 Loxley ตรวจ Internal Cabling (Roadside) | 2025-10-15 | 2025-10-15 |  |  | Y | [6 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 BGSR ตรวจ Official Cabling (Roadside) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Roadside) | 2025-10-17 | 2025-10-19 |  |  |  |  | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Cabling (Roadside) | 2025-10-15 | 2025-10-19 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Steel Pole (Roadside) | 2025-10-19 | 2025-10-19 | [6 empty] | Y |  |  | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST
INST | [5 empty] | งาน Scale House
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 ติดตั้ง Equipment (Scale House) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 Loxley ตรวจ Internal Equipment (Scale House) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Saraburi | 38+700 | 7 | ด่าน M6-4 BGSR ตรวจ Official Equipment (Scale House) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 ติดตั้ง Equipment (Scale House) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 Loxley ตรวจ Internal Equipment (Scale House) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kaeng Khoi | 53+780 | 14 | ด่าน M6-5 BGSR ตรวจ Official Equipment (Scale House) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 งาน Cabling (Scale House) | 2025-10-13 | 2025-10-13 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 Loxley ตรวจ Internal Cabling (Scale House) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 BGSR ตรวจ Official Cabling (Scale House) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Scale House) | 2025-10-17 | 2025-10-19 |  |  |  |  | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 Loxley ตรวจ Internal Cabling (Scale House) | 2025-10-14 | 2025-10-14 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 BGSR ตรวจ Official Cabling (Scale House) | 2025-10-17 | 2025-10-17 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Scale House) | 2025-10-17 | 2025-10-19 |  |  |  |  | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Cabling (Scale House) | 2025-10-15 | 2025-10-19 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST
Week 2 (WK No.42) | [6 empty] | 2025-10-20 | 2025-10-26 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26
INST | [5 empty] | งาน Roadside
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Cabling (Roadside) | 2025-10-20 | 2025-10-20 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Steel Pole (Roadside) | 2025-10-20 | 2025-10-20 | Y | [8 empty] | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 Loxley ตรวจ Internal Cabling (Roadside) | 2025-10-21 | 2025-10-21 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 BGSR ตรวจ Official Cabling (Roadside) | 2025-10-24 | 2025-10-24 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Roadside) | 2025-10-20 | 2025-10-26 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Roadside) | 2025-10-20 | 2025-10-26 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Cabling (Roadside) | 2025-10-22 | 2025-10-26 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Steel Pole (Roadside) | 2025-10-26 | 2025-10-26 | [6 empty] | Y |  |  | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST
INST | [5 empty] | งาน Scale House
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 งาน Cabling (Scale House) | 2025-10-20 | 2025-10-20 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 Loxley ตรวจ Internal Cabling (Scale House) | 2025-10-21 | 2025-10-21 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 BGSR ตรวจ Official Cabling (Scale House) | 2025-10-24 | 2025-10-24 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Scale House) | 2025-10-20 | 2025-10-26 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Scale House) | 2025-10-20 | 2025-10-26 | Y | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Cabling (Scale House) | 2025-10-22 | 2025-10-26 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST
Week 3 (WK No.43) | [6 empty] | 2025-10-27 | 2025-11-02 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02
INST | [5 empty] | งาน Roadside
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Roadside) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 Loxley ตรวจ Internal Equipment (Roadside) | 2025-10-28 | 2025-10-28 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 BGSR ตรวจ Official Equipment (Roadside) | 2025-10-30 | 2025-10-30 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Roadside) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 Loxley ตรวจ Internal Equipment (Roadside) | 2025-10-28 | 2025-10-28 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 BGSR ตรวจ Official Equipment (Roadside) | 2025-10-30 | 2025-10-30 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Steel Pole (Roadside) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Aomsin Traisuppapaisan | P.A.PRODUCT | 085-8367801
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Cabling (Roadside) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 Loxley ตรวจ Internal Cabling (Roadside) | 2025-10-29 | 2025-10-29 |  |  | Y | [6 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 BGSR ตรวจ Official Cabling (Roadside) | 2025-10-31 | 2025-10-31 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 ติดตั้ง Equipment (Roadside) | 2025-10-28 | 2025-11-02 |  | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Wang Noi | 10+800 | 4 | ด่าน M6-2 ตรวจ Comment Equipment (Roadside) | 2025-10-31 | 2025-10-31 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Hin Kong | 33+100 | 6 | ด่าน M6-3 ตรวจ Comment Equipment (Roadside) | 2025-10-31 | 2025-10-31 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Bang Pa-In | 4+750 | 3 | ด่าน M6-1 งาน Cabling (Roadside) | 2025-10-29 | 2025-11-02 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST
INST | [5 empty] | งาน Scale House
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 ติดตั้ง Equipment (Scale House) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 Loxley ตรวจ Internal Equipment (Scale House) | 2025-10-28 | 2025-10-28 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Pak Chong | 110+500 | 23 | ด่าน M6-7 BGSR ตรวจ Official Equipment (Scale House) | 2025-10-30 | 2025-10-30 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 ติดตั้ง Equipment (Scale House) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 Loxley ตรวจ Internal Equipment (Scale House) | 2025-10-28 | 2025-10-28 |  | Y | [7 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Si Khiu | 154+960 | 37 | ด่าน M6-8 BGSR ตรวจ Official Equipment (Scale House) | 2025-10-30 | 2025-10-30 |  |  |  | Y | [5 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 งาน Cabling (Scale House) | 2025-10-27 | 2025-10-27 | Y | [8 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 Loxley ตรวจ Internal Cabling (Scale House) | 2025-10-29 | 2025-10-29 |  |  | Y | [6 empty] | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Muak Lek | 77+800 | 20 | ด่าน M6-6 BGSR ตรวจ Official Cabling (Scale House) | 2025-10-31 | 2025-10-31 |  |  |  |  | Y |  |  |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Kham Thale Sor | 185+125 | 11 | ด่าน M6-9 ติดตั้ง Equipment (Scale House) | 2025-10-28 | 2025-11-02 |  | Y | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST | Weighing | Weight Station | Bang Pa-In | 4+750 | 3 | ด่าน M6-1 งาน Cabling (Scale House) | 2025-10-29 | 2025-11-02 |  |  | Y | Y | Y | Y | Y |  |  | Mr.Chayakrit Namjairak | P.A.PRODUCT | 084-0985666
INST
Formulas:
End = [Date]+6
Week = [Date]
T U E = [Week]+1
W E D = [T U E]+1
T H U = [W E D]+1